## Kumar
Sl No | Date | Task | Associate | Remarks
1 | 2018-07-12 | Log in and Log Out | Venkat | 70% of task is completed,
2 | 2018-07-12 | WebApi for Initial deafault view | Krishna | Started the work
3 | 2018-07-12 | Stored Procedures & Tables Creation | Krishna | most part of the work is done, Rajesh is closely monitoring the day today work of krishna
4 | 2018-07-12 | Suraj is on Leave | Suraj
5 | 2018-07-12 | Working on TFS server setup | Kumar | Coordinating with the overall project and filling the gaps: providing the angular material to Suraj, verifying the angular code, and WebApi code of Krishna
6 | 2018-07-12 | Self Learning Angular | Kumar | maximilian schwarzmüller
7 | 2018-07-13 | Log in and Log Out Validation | Venkat | completed, need to take webapi code from Krishna
8 | 2018-07-13 | WebApi for Initial deafault view | Krishna | Continuing to work
9 | 2018-07-13 | Change Password task | Suraj | Started to work on the task
9 | 2018-07-13 | Self Learning Angular and helping Suraj to Pickup Angular | Kumar | assigned a task "change password" to suraj, and coordinating with him
10 | 2018-07-13 | Working on TFS server setup | Kumar | tfs server setup temp on my laptop, but facing few issues while installing
11 | 2018-07-13 | Team Coordination | Kumar | Discussed few pain points with Rajesh
12 | 2018-07-13 | Setup IIS | Kumar
13 | 2018-07-16 | working on WebApi connectivity issue | Venkat | Kumar, asked 2 people not to work on same issue, let the team carry on with other tasks meanwhile, and let Kumar work on fixing the issue. Team needs to reproduce the issue to kumar and from there, Kumar would continue to fix it
14 | 2018-07-16 | working on WebApi connectivity issue | Krishna
15 | 2018-07-16 | Working on Change Password Task | Suraj
16 | 2018-07-16 | Working on the Roadblock facing by Krishna & Venkat with WebApi | Kumar
17 | 2018-07-17 | CORS Issue resolved | Kumar | https://stackoverflow.com/questions/36258959/cors-enabled-but-response-for-preflight-has-invalid-http-status-code-404-when-po
18
19 | 2018-07-18 | Met Ajay, discrepency on the role | Kumar | Kumar might have to get release from the project (MDT). Before releasing, Rajesh has assigned few tasks to complete: TFS setup on Windows Server , Online VSTS setup
20
21 | 2018-07-18 | Worked on providing vsts version control to the venkat | Kumar | task assigned by Rajesh
22 | 2018-07-19 | Working on providing vsts version control to the Krishna. Worked for Half day | Kumar | task assigned by Rajesh
23 | 2018-07-20 | Leave
24 | 2018-07-23 | Working on task vsts for WebApi and Suraj wants me to look into design issues | Kumar | task assigned by Rajesh, and working on some issue in angular code as asked for help with me by Suraj
25 | 2018-07-24 | working on lock user task | Kumar | Task assigned by Rajesh
26 | 2018-07-24 | continue to work on yday task, and later need todo unit testing | Kumar
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98

## Venkat
Sl No | Date | What work we completed yesterday | What work we are going to do for today | Any road blocks or challenges | Remarks
1 | 2018-07-18 | I need to fetch data from webapi and bind to table. | I am Created table for system configuration, created change password page and router configuration for change password, and completed Basic inputs.
2 | 2018-07-19 | I completed binding data to table and table layout(nested column). | I need to work on dropdowns in Sub System column and work on total cost column, Show Hide the cost column.
3 | 2018-07-20 |  |  |  | Yesterday I installed TFS client in my machine and I connected to MDT cloud project successfully.
4 |  |  |  |  | No need to go browser to drag and drop files and commit the code. If you install TFS client in our machine it will automatically connected to MDT cloud by default if have a access to MDT cloud project.
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142

## Suraj
Sl No | Date | What work we completed yesterday | What work we are going to do for today | Any road blocks or challenges | Remarks
1 | 2018-07-16 | Today I’m working on Change password task on landing page.
2 | 2018-07-17 | Working on change profile picture task
3 | 2018-07-18 | Today i'm going to worked on change password to connect with web api.
4 | 2018-07-19 | Today I’m going to work on side menu in landing page.
5 | 2018-07-20 | Worked Side menu, data bind is ok, but some design issues |  | Design Issues
6 |  |  |  | Asked Kumar's help for design issues
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512

## Krishna
Sl No | Date | What work we completed yesterday | What work we are going to do for today | Any road blocks or challenges | Remarks
1 | 2018-07-16 | I worked in Login WebAPI on Friday and completed that one. | Today I am working in Change password WebAPI | On Friday we were facing some CORS issue while calling POST method from Angular but It is working from PostMan tool. The Issue is still there.
2 | 2018-07-17 | I worked in Change password WebAPI and Forgot Password WebAPI. | As per discussion with Rajesh, I will work on making WebAPI to display Configuration System details in main page for sale. I also have add entries into database for Grid | While creating WebAPI for forgot password, I need to implement Notification system to send an email to user with new password. To implement notification system, I need smtp details Like SMTP Name, From email address and Password etc.
3 | 2018-07-18 | I worked on making WebAPI to display Configuration System details in main page for sale based on package. I also added entries into database for Grid Frequency Basic Input options. | I will work to update latest data into DB after that I will Add table tblSoulution and create relationship between Package and Solution. Then I will create procedure to get side menu and also will create WebAPI to get side menu done | no road blocks
4 | 2018-07-19 | As discussion with rajesh I started working on data update in DB. As per discussion with rajesh, I added TYPE column in tables tblPACKAGE_SYSTEM_EQUIPMENT” and “tblPKG_SYSTEM_EQP_VARIANT” to make equipment and equipment variants mandatory/optional. I updated the tblSystem and corrected the data. I also updated tblPACKAGE_SYSTEM table and inserted the data into TYPE field as Mandatory/Optional. I updated tblEquipment and tblEQUIPMENT_VARIANT_OPTIONS respectively. | I will work to update latest data into DB after that I will Add table tblSoulution and create relationship between Package and Solution. Then I will create procedure to get side menu and also will create WebAPI to get side menu done. | no road blocks
5 | 2018-07-20 | As discussion with rajesh I started working on data update in DB. As per discussion with rajesh, I added TYPE column in tables tblPACKAGE_SYSTEM_EQUIPMENT” and “tblPKG_SYSTEM_EQP_VARIANT” to make equipment and equipment variants mandatory/optional. I updated the tblSystem and corrected the data. I also updated tblPACKAGE_SYSTEM table and inserted the data into TYPE field as Mandatory/Optional. I updated tblEquipment and tblEQUIPMENT_VARIANT_OPTIONS respectively. | I am continue working with pending data updates | no road blocks
6 | 2018-07-23 | I updated the data into below tables. 1. tblSYSTEM 2. tblEQUIPMENT 3. tblSYSTEM_EQUIPMENT 4. tblSYSTEM_EQUIPMENT_VARIANT 5. tblEQUIPMENT_VARIANT_OPTIONS 6. tblPACKAGE_SYSTEM_EQUIPMENT 7. tblPKG_SYSTEM_EQP_VARIANT | I am continue working with pending data updates . | There are some discrepancy with data which needs to discuss with Rajesh
7 | 2018-07-24 | I Prepared and updated costing data in tblSUPPLIER_EQUIPMENT_COSTS. | I am continue working with pending data updates for STANDARD/OPTIONAL. Once it will complete I will start working on Stored Proc and WebAPI to display Sub System details for package in UI as per latest data. | no road blocks
8 | 2018-07-25 | a. I updated pending data into DB for Package. b. I worked in Package System Stored Proc and WebAPI to get corrected based on new metadata. c. I worked in Authentication and applied only one WebAPI for now so that it can be tested from frontend. It will be tested from frontend, I will apply authentication in all WebAPI. d. As per discussion with Rajesh, I added a column IS_MANDATORY in tblPACKAGE_SYSTEM and updated all the data from TYPE column to IS_MANDATORY in table. e. I again worked on Package System detail Stored Proc and WebAPI to get them corrected. | a. I need to create table tblPACKAGE_SYSTEM_WORKS and tblSUPPLIER_WORK_COST. b. I have insert data into both tables which are created c. I need to implement the logic lock account logic in Stored Proc level which Kumar has already created in code level. d. I will work in Package System Detail Stored Proc and WebAPI based on data added into tables tblPACKAGE_SYSTEM_WORKS and tblSUPPLIER_WORK_COST to display Electical & Mechanical Cost in landing page grid. | no road blocks
9 |  |  |  | no road blocks
10 |  |  |  | no road blocks
11 |  |  |  | no road blocks
12 |  |  |  | no road blocks
13 |  |  |  | no road blocks
14 |  |  |  | no road blocks
15 |  |  |  | no road blocks
16 |  |  |  | no road blocks
17 |  |  |  | no road blocks
18 |  |  |  | no road blocks
19 |  |  |  | no road blocks
20 |  |  |  | no road blocks
21 |  |  |  | no road blocks
22 |  |  |  | no road blocks
23 |  |  |  | no road blocks
24 |  |  |  | no road blocks
25 |  |  |  | no road blocks
26 |  |  |  | no road blocks
27 |  |  |  | no road blocks
28 |  |  |  | no road blocks
29 |  |  |  | no road blocks
30 |  |  |  | no road blocks
31 |  |  |  | no road blocks
32 |  |  |  | no road blocks
33 |  |  |  | no road blocks
34 |  |  |  | no road blocks
35 |  |  |  | no road blocks
36 |  |  |  | no road blocks
37 |  |  |  | no road blocks
38 |  |  |  | no road blocks
39 |  |  |  | no road blocks
40 |  |  |  | no road blocks
41 |  |  |  | no road blocks
42 |  |  |  | no road blocks
43 |  |  |  | no road blocks
44 |  |  |  | no road blocks
45 |  |  |  | no road blocks
46 |  |  |  | no road blocks
47 |  |  |  | no road blocks
48 |  |  |  | no road blocks
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207